## Sheet1
[P4DS] Final Project
Members | 19127037 | Võ Bách Khôi
| 19127303 | Hình Ích Trình
Main Topic | University Rankings
Date | Platform | Description | Detail | Deadline
2021-12-25 | Google meet | Find the main topic for the project | All members | Before next meeting
2021-12-26 | Messenger | Main topic is University Rankings and start to find the public datasets | All members | Before next meeting
2021-12-30 | Google meet | Team agrees to use 3 public datasets: World University Rankings, “American University Data” IPEDS Dataset, Startup Founder Valuations Dataset and start to sketchily explore these datasets to ask meaningful questions | Each member asks 2 questions | Before next meeting
2022-01-02 | Google meet | Finish section "Meaningful Questions" with 4 questions and start to analyze the data to answer them. Moreover, the team decided to use English as the main language. | Each member writes and processes in his own notebook | Before next meeting
2022-01-04 | Messenger | Discuss difficulties encountered | All members
2022-01-10 | Google meet | Basic completion of content requirements. Read, Comment and Understand each other notebook | Read, Comment and Understand each other notebook | Before next meeting
2022-01-12 | Messenger | Comment each other | All members
2022-01-13 | Messenger | Merge notebooks into 1 file and finish the project | Ích Trình: writes HowToRun and Bách Khôi: merges notebooks, finishes remaining requirements | Before Jan 14, 2022
2022-01-14 | Google meet | Revise the project and practice presentation | All members
2022-01-15 | Google meet | Revise the project and practice presentation | All members